## Sheet1
# | Lookup# | Brand | Cat | Project Name | Description | Model # | Note | MSRP | Show | MP1 | Launch | FY Period | Status | Comment | PIF Date Submitted | PIF Date Accepted | Greenlight Date | Greenlight Target PM1 | MP1 Date Actual | BluOS | 0 | 0 | 0
132 | 100117 | NAD | CCLA | CC3380 | D3045/C338 replacement;CL2250 poweramp. C399 updated display, 1 x MDC2 slot | Classic Compact ID |  | 799 | MHE 2025 | 2025-12-31 | 2026-03-01 | FY26 | Concept Approved
103 | 100127 | NAD | CCLA | CC2550 | Poweramp section of CL3380; 2 x 80; 1 x 300 bridgable | Classic Compact ID |  | 699 | MHE 2025 | 2025-12-31 | 2026-03-01 | FY26 | Concept Approved
154 | 100147 | NAD | NCLA | C3990 | C399 Replacement. Bridgeable: Power amp C2990 | New Classic ID |  | 2499 | MHE 2025 | 2025-12-03 | 2026-02-01 | FY26 | Concept Approved
121 | 100120 | NAD | NCLA | C2990 | C298 Replacement - 2 x 180W bridgeable same as C3990 poweramp section | New Classic ID |  | 1999 | MHE 2025 | 2025-12-03 | 2026-02-01 | FY26 | Concept Approved
116 | 110106 | NAD CI | CI | PA 16-80 M | 16 channel Matrix Amplifier, DSP, Dante + Dirac |  |  | 3499 | ISE 2026 | 2025-12-03 | 2026-02-01 | FY26 | Concept Approved | PIF completed | 2024-01-14 |  |  |  |  | No
205 | 110123 | NAD CI | CI | PA 4-240 M | 4 channel Matrix Amplifier, DSP, Dante + Dirac |  |  | 1999 | ISE 2026 | 2025-12-03 | 2026-02-01 | FY26 | Concept Approved | PIF completed | 2024-10-28 |  |  |  |  | No
210 | 110128 | NAD CI | CI | PA 8-80 M | 8 channel Matrix Amplifier, DSP, Dante + Dirac |  |  | 2499 | ISE 2026 | 2025-12-03 | 2026-02-01 | FY26 | Concept Approved | PIF completed | 2024-10-28 |  |  |  |  | No
125 | 300125 | BLS | PULSE | PULSE DUO | Bluesound iQ | P630 | Hero | 1499 |  | 2025-11-03 | 2026-01-01 | FY26 | Concept Approved
84 | 400107 | BPR | PRO | PS1 | Paging interface phase 1 |  | Priority 3 | 499 | CEDIA 2025 | 2025-11-01 | 2025-12-01 | FY26 | Concept Approved | Waiting to determine external development resource | 2020-07-07 |  |  |  |  | Yes
100 | 300115 | BLS | PULSE | PULSE FLEX | AM Logic; re-design with similar footprint/size, more like Pulse M style; multi-use | P130 | Hero | 279 | Munich 2025 | 2025-08-03 | 2025-10-01 | FY26 | Concept Approved |  | 2024-09-09 |  |  |  |  | Yes
102 | 300119 | BLS | ACC | BP130 | Re-design of Flex Battery Pack | BP130 |  | 99 | Munich 2025 | 2025-08-03 | 2025-10-01 | FY26 | Concept Approved
91 | 100122 | NAD | MSTR | M880 | 800W Mono - M28 case upgraded; Single VU;??? (2/3 width??) |  |  | 7499 | MHE 2025 | 2025-08-02 | 2025-10-01 | FY26 | Concept Approved
136 | 100129 | NAD | CLAS | C569 | Mid-range CD C538 based; 9039q2m DAC; Qrono |  |  | 799 | MHE 2025 | 2025-08-02 | 2025-10-01 | FY26 | Concept Approved
107 | 300107 | BLS | PULSE | PULSE CINEMA | iMX.8; 3.1 w/ctr; new ID; length +5" (match 55" TV); upfiring speakers | P535 | Hero | 1199 | Munich 2025 | 2025-07-04 | 2025-09-01 | FY26 | Greenlight |  | 2024-04-11 | 2024-07-16 | 2024-09-16 | 2025-07-01 |  | Yes
104 | 300110 | BLS | PULSE | PULSE CINEMA MINI | iMX.8; UI; new ID; 2-channel with virtual Atmos, for 30-50" screens | P435 |  | 699 | Munich 2025 | 2025-07-04 | 2025-09-01 | FY26 | Greenlight |  | 2024-04-11 | 2024-07-16 | 2024-09-16 | 2025-07-01 |  | Yes
93 | 100131 | NAD | CLAS | C589 | C568 successor, ES9039 DAC, MQA, Balanced; Transitions to new styling |  |  | 1299 | MHE 2025 | 2025-07-03 | 2025-09-01 | FY26 | Greenlight
94 | 100133 | NAD | CLAS | C599 | C588 Replacement; higher price; electr. 33/45; double glass; Blue or Bronze cartridge |  |  | 1299 | MHE 2025 | 2025-07-03 | 2025-09-01 | FY26 | Concept Approved
108 | 100132 | NAD | CLAS | C3030 | C3050 looks; just vinyl wrap over metal cover; Class D, BT, MDC2?? | Vintage ID |  | 999 | MHE 2025 | 2025-07-03 | 2025-09-01 | FY26 | Concept Approved
117 | 100116 | NAD | MSTR | M850 | 2 x 400 Purifi; seperate PS L/ R/ gain section, Mech VU meters (M28 Chassis) |  |  | 8499 | MHE 2025 | 2025-07-03 | 2025-09-01 | FY26 | Concept Approved
110 | 110108 | NAD CI | CI | S4 | replacement ci580v2, modular 4 zone streamer |  |  | 1249 | CEDIA 2025 | 2025-07-03 | 2025-09-01 | FY26 | Greenlight | PIF submitted, project ko when visiting factory nov'24 | [5 empty] | Yes
111 | 110114 | NAD CI | CI | H4 | CI Hub for in rack |  |  | 499 | CEDIA 2025 | 2025-07-03 | 2025-09-01 | FY26 | Greenlight | PIF submitted, project ko when visiting factory nov'24 | 2024-01-14 |  |  |  |  | Yes
214 | 110132 | NAD CI | CI | H2 | CI hub for TV |  |  | 349 | CEDIA 2025 | 2025-07-03 | 2025-09-01 | FY26 | Concept Approved | PIF submitted, project ko when visiting factory nov'24 | 2024-10-04 |  |  |  |  | Yes
76 | 100137 | NAD | CLAS | C549 | C558 Replacement; El. Switching, same price level |  |  | 699 | MHE 2025 | 2025-07-03 | 2025-09-01 | FY26 | Concept Approved
57 | 400119 | BPR | PRO | Pro Hub | Pro Hub connections and internal storage, Phase 2 failover B100S Mech ID |  | Priority 4 | 299 | InfoComm 25 | 2025-07-01 | 2025-07-01 | FY26 | On Hold | Will do some repackaging for next production run | 2022-07-01
92 | 100144 | NAD | MSTR | M600 | Streamer section M66 + MQA Qrono; 12S; in Black & Silver |  |  | 4499 | MHE 2025 | 2025-06-02 | 2025-08-01 | FY26 | Greenlight
98 | 300117 | BLS | NODE | POWERNODE | 3-Channel Powernode / Simple AV; Axign amp w GaN, 100W 2-channel, | N331 | Hero | 999 | Munich 2025 | 2025-05-02 | 2025-06-01 | FY26 | Concept Approved |  | 2024-10-29 |  |  |  |  | Yes
89 | 100121 | NAD | MSTR | M33 V2 | As M33; +Bal out -2nd speaker +ES9039PRO Qrono + ESS FoQus + new Eigentakt(?) |  |  | 5999 | MHE 2025 | 2025-04-02 | 2025-06-01 | FY26 | Greenlight
90 | 100128 | NAD | MSTR | M23 V2 | As M23; new Eigentakt; trig.out; also in black (match M33V2 in black?) |  |  | 3499 | MHE 2025 | 2025-04-02 | 2025-06-01 | FY26 | Greenlight
80 | 230103 | PSB HP | HP | M4U X | High-Resolution Wireless Over Headphones; Sonical platform; MQA support |  |  | 799 | TBC | 2025-03-02 | 2025-05-01 | FY26 | Concept Approved
105 | 110112 | NAD CI | CI | PA 4-60 | 4 x 60 watt power amplifier, modular |  |  | 799 | ISE 2025 | 2025-03-02 | 2025-05-01 | FY26 | Greenlight | quoted received, started. ES1 shipping late sept, MP1 pushed out to May 2025. checking | 2024-01-14 |  | 2024-04-30 |  |  | no
203 | 110115 | NAD CI | CI | S1 | Single zone BluOS streamer, modular |  |  | 749 | ISE 2025 | 2025-03-02 | 2025-05-01 | FY26 | Greenlight | quote received in July, awaiting block digrams and design in sept. investigatingDSP for aes67 support following cedia | 2024-01-14 |  | 2024-04-30 |  |  | Yes
615 | 110105 | NAD CI | CI | SA2-120 | BluOS Streaming Amp, step up from CI720v (not replacement) |  |  | 1299 | ISE 2025 | 2025-03-02 | 2025-05-01 | FY26 | Greenlight | quote received in July, awaiting block digrams and design in sept. investigatingDSP for aes67 support following cedia | 2024-01-14 |  | 2024-04-30 |  |  | Yes
87 | 110104 | NAD CI | AVR | T799 | MDC 11.2 100W w/BluOS |  |  | 6999 | ISE 2025 | 2025-03-02 | 2025-05-01 | FY26 | Greenlight | signoff on boards for PP needed in early october, PP in late december, Bete testing to begin first week of january |  | 2022-02-08 |  |  |  | Yes
78 | 400127 | BPR | PRO | Teknion | SOUNDCOVE-Chair Solution (OEM) |  |  | 190 | N/A | 2025-03-01 | 2025-03-01 | FY26 | Concept Approved
74 | 110119 | NAD CI | CI | CI 8-150 DSP V2 | improve UI,& monitoring API, add temp sensors, channel sleep, DSP, pricing and margin reposition |  | V2 Possible name update | 3799 | CEDIA 2024 | 2024-12-31 | 2025-03-01 | FY25 | Greenlight | underway, UI in progress, V2 software will launch sept 2024, v2 hardware Q1 2025, review MP date Nov. | 2024-02-14 |  | 2024-04-03 |  |  | no
73 | 110118 | NAD CI | CI | CI 16-60 DSP V2 | improve UI,& monitoring API, add temp sensors, channel sleep, DSP, pricing and margin reposition |  | V2 Possible name update | 2399 | CEDIA 2024 | 2024-12-31 | 2025-03-01 | FY25 | Greenlight | underway, UI in progress, V2 software will launch sept 2024, v2 hardware Q1 2025, review MP date Nov. | 2024-02-14 |  | 2024-04-03 |  |  | No
75 | 110120 | NAD CI | CI | CI 8-120 DSP V2 | improve UI,& monitoring API, add temp sensors, channel sleep, DSP, pricing and margin reposition |  | V2 Possible name update | 2799 | CEDIA 2024 | 2024-12-31 | 2025-03-01 | FY25 | Greenlight | underway, UI in progress, V2 software will launch sept 2024, v2 hardware Q1 2025, review MP date Nov. | 2024-02-14 |  | 2024-04-03 |  |  | no
88 | 200124 | PSB | SPKR | SubSeries BP12 | Flagship PSB Subwoofer |  | initial design underway | 3999 | CEDIA 2024 | 2024-12-03 | 2025-02-01 | FY25 | Concept Approved | PP1 slated for last week of October | 2024-01-17
77 | 300123 | BLS | NODE | NODE ICON | iMX.8; high-performance Node, with display, with balanced outputs, extra inputs, THX amp, 2x ESS DAC | N530 | Hero | 999 | Munich 2024 | 2024-10-02 | 2024-11-01 | FY25 | Complete |  | 2023-11-17 | 2024-03-18 | 2024-03-25 | 2024-10-01 | 2024-11-30 | Yes
69 | 100139 | NAD | MSTR | M10 V3 | As V2; +phono +ES9039 +Dirac BC |  | Masters | 2499 | MHE 2024 | 2024-08-02 | 2024-10-01 | FY25 | Greenlight | At KA for FOB quote |  |  | 2023-09-29 | 2024-09-01
67 | 300116 | BLS | NODE | NODE | iMX.8; replacement for N130, ESS DAC, THX headphone amp | N132 | Hero | 549 | Munich 2024 | 2024-07-03 | 2024-09-01 | FY25 | Complete |  | 2023-11-10 | 2024-03-21 | 2024-03-24 | 2024-06-01 | 2024-07-31 | Yes
66 | 400115 | BPR | PRO | CP300 | Color LCD Controller |  |  | 399 | CEDIA 2024 | 2024-07-01 | 2024-08-01 | FY25 | Greenlight | Buy Android tablet and resell |  |  | 2024-06-01 |  | 2024-07-01 | No
65 | 100138 | NAD | CLAS | C700 V2 | As C700; +phono +ES9028 +BluOS surround +remote | . |  | 1599 | MHE 2024 | 2024-06-02 | 2024-08-01 | FY25 | Greenlight | At KA for FOB quote |  |  | 2023-09-29 | 2024-07-01
63 | 300121 | BLS | NODE | NODE NANO | iMX.8; entry-point streaming zone; ESS DAC; streamer-only; DTC primary | N030 | Hero | 299 | Munich 2024 | 2024-05-03 | 2024-08-01 | FY25 | Complete |  | 2023-07-14 | 2023-07-14 | 2023-07-14 | 2024-04-01 | 2024-05-31 | Yes
59 | 100115 | NAD | CLAS | C379 (was C369) | 2 x 80, UCD, MDC2, new DAC, ID, display | . | Old ID | 999 | MHE 2024 | 2024-05-02 | 2024-07-01 | FY25 | Greenlight | Hansong ready for production | [5 empty] | MDC