## Sheet1
# | Lookup# | Brand | Cat | Project Name | Description | Model # | Note | MSRP | Show | MP1 | Launch | FY Period | Status | Comment | PIF Date Submitted | PIF Date Accepted | Greenlight Date | Greenlight Target PM1 | MP1 Date Actual
78 | 400127 | BPR | PRO | Teknion | SOUNDCOVE-Chair Solution (OEM) |  |  | 190 | N/A | 2025-03-01 | 2025-03-01 | FY26 | Concept Approved
80 | 230103 | PSB HP | HP | M4U X | High-Resolution Wireless Over Headphones; Sonical platform; MQA support |  |  | 799 | TBC | 2025-03-02 | 2025-05-01 | FY26 | Concept Approved
105 | 110112 | NAD CI | CI | PA 4-60 | 4 x 60 watt power amplifier, modular |  |  | 799 | ISE 2025 | 2025-03-02 | 2025-05-01 | FY26 | Greenlight | quoted received, started. ES1 shipping late sept, MP1 pushed out to May 2025. checking | 2024-01-14 |  | 2024-04-30 |  |  | no
203 | 110115 | NAD CI | CI | S1 | Single zone BluOS streamer, modular |  |  | 749 | ISE 2025 | 2025-03-02 | 2025-05-01 | FY26 | Greenlight | quote received in July, awaiting block digrams and design in sept. investigatingDSP for aes67 support following cedia | 2024-01-14 |  | 2024-04-30 |  |  | Yes
615 | 110105 | NAD CI | CI | SA2-120 | BluOS Streaming Amp, step up from CI720v (not replacement) |  |  | 1299 | ISE 2025 | 2025-03-02 | 2025-05-01 | FY26 | Greenlight | quote received in July, awaiting block digrams and design in sept. investigatingDSP for aes67 support following cedia | 2024-01-14 |  | 2024-04-30 |  |  | Yes
87 | 110104 | NAD CI | AVR | T799 | MDC 11.2 100W w/BluOS |  |  | 6999 | ISE 2025 | 2025-03-02 | 2025-05-01 | FY26 | Greenlight | signoff on boards for PP needed in early october, PP in late december, Bete testing to begin first week of january |  | 2022-02-08 |  |  |  | Yes
69 | 100139 | NAD | MSTR | M10 V3 | As V2; +phono +ES9039 +Dirac BC |  | Masters | 2499 | MHE 2024 | 2024-08-02 | 2024-10-01 | FY25 | Greenlight | At KA for FOB quote |  |  | 2023-09-29 | 2024-09-01
77 | 300123 | BLS | NODE | NODE ICON | iMX.8; high-performance Node, with display, with balanced outputs, extra inputs, THX amp, 2x ESS DAC | N530 | Hero | 999 | Munich 2024 | 2024-10-02 | 2024-11-01 | FY25 | Complete |  | 2023-11-17 | 2024-03-18 | 2024-03-25 | 2024-10-01 | 2024-11-30 | Yes
88 | 200124 | PSB | SPKR | SubSeries BP12 | Flagship PSB Subwoofer |  | initial design underway | 3999 | CEDIA 2024 | 2024-12-03 | 2025-02-01 | FY25 | Concept Approved | PP1 slated for last week of October | 2024-01-17
74 | 110119 | NAD CI | CI | CI 8-150 DSP V2 | improve UI,& monitoring API, add temp sensors, channel sleep, DSP, pricing and margin reposition |  | V2 Possible name update | 3799 | CEDIA 2024 | 2024-12-31 | 2025-03-01 | FY25 | Greenlight | underway, UI in progress, V2 software will launch sept 2024, v2 hardware Q1 2025, review MP date Nov. | 2024-02-14 |  | 2024-04-03 |  |  | no
73 | 110118 | NAD CI | CI | CI 16-60 DSP V2 | improve UI,& monitoring API, add temp sensors, channel sleep, DSP, pricing and margin reposition |  | V2 Possible name update | 2399 | CEDIA 2024 | 2024-12-31 | 2025-03-01 | FY25 | Greenlight | underway, UI in progress, V2 software will launch sept 2024, v2 hardware Q1 2025, review MP date Nov. | 2024-02-14 |  | 2024-04-03 |  |  | No
75 | 110120 | NAD CI | CI | CI 8-120 DSP V2 | improve UI,& monitoring API, add temp sensors, channel sleep, DSP, pricing and margin reposition |  | V2 Possible name update | 2799 | CEDIA 2024 | 2024-12-31 | 2025-03-01 | FY25 | Greenlight | underway, UI in progress, V2 software will launch sept 2024, v2 hardware Q1 2025, review MP date Nov. | 2024-02-14 |  | 2024-04-03 |  |  | no